## Guide
RenewableMIS — Monthly MIS: Actual vs Annual Operating Plan (AOP)
Demo workbook built around a renewable-energy MIS automation brief: a monthly
management report comparing generation and revenue actually achieved against
the Annual Operating Plan baseline, by site, state, technology and month.
HOW TO REFRESH (the automation this demo proves)
1. Drop next month's site generation/revenue export into Raw_Plan / Raw_Actual
(same columns, one row per site-month). Extend the SUMIFS ranges below.
2. Monthly, State, Technology, Dashboard and Checks all recalculate — no
hard-coded totals anywhere in the summary sheets.
3. In Power BI, point the model at the same two raw tables; see
powerbi/MEASURES.md for the DAX equivalents of every KPI.
SHEET MAP
Dashboard — 10 headline KPIs + 3 charts (technology mix, monthly trend).
Monthly — planned vs actual by month, with availability from outage hours.
State — planned vs actual by state (9 Indian states + UAE + Singapore).
Technology — planned vs actual by Solar / Wind / Hybrid / Rooftop.
Sites — the 17-site portfolio: capacity (MW) and tariff (Rs/kWh).
Raw_Plan / Raw_Actual — one row per site-month; derived columns are formulas.
Checks — 8 integrity checks; every Status must read PASS.
DATA NOTE
All figures are fictional, generated deterministically (seed 20261029) for
this demo. Two documented events are baked in: heavy curtailment at Kutch
Wind Farm in Jul 2026 (18% of planned) and a 120-hour outage at Kamuthi
Solar Park in Sep 2026. Revenue is in Rs lakh (MWh x tariff / 100).
Availability % = 1 - outage hours / (sites x days x 24).

## Dashboard
RenewableMIS — Portfolio Dashboard (Apr-Oct 2026)
All values are live formulas over Raw_Plan / Raw_Actual.
Sites in portfolio
Total Planned Generation (MWh)
Total Actual Generation (MWh)
Generation Achievement %
Planned Revenue (Rs lakh)
Actual Revenue (Rs lakh)
Revenue Achievement %
Curtailment (MWh)
Curtailment % of Planned
Total Outage Hours
Weighted Availability %
Charts below are wired to Technology / Monthly — they move with the raw data.

## Sites
SiteID | Site | State | Technology | CapacityMW | TariffRsPerKWh
S01 | Jodhpur Solar Park | Rajasthan | Solar | 50 | 2.95
S02 | Kutch Solar Park | Gujarat | Solar | 40 | 2.85
S03 | Solapur Solar Park | Maharashtra | Solar | 25 | 3.1
S04 | Pavagada Solar Park | Karnataka | Solar | 30 | 3.05
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 20 | 3.2
S06 | Mahbubnagar Solar Park | Telangana | Solar | 15 | 3
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 35 | 2.9
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 45 | 2.8
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 10 | 3.3
W01 | Kutch Wind Farm | Gujarat | Wind | 30 | 3.6
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 25 | 3.75
W03 | Satara Wind Farm | Maharashtra | Wind | 20 | 3.85
W04 | Chitradurga Wind Farm | Karnataka | Wind | 15 | 3.7
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 60 | 3.15
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 40 | 3.1
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2 | 3.4
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 1.5 | 3.5

## Raw_Plan
SiteID | Site | State | Technology | Month | PlannedMWh | PlannedRevenueLakh
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-04 | 7560 | 223.02
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-05 | 8184 | 241.43
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-06 | 6840 | 201.78
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-07 | 6696 | 197.53
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-08 | 7068 | 208.51
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-09 | 7560 | 223.02
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-10 | 8184 | 241.43
S02 | Kutch Solar Park | Gujarat | Solar | 2026-04 | 6048 | 172.37
S02 | Kutch Solar Park | Gujarat | Solar | 2026-05 | 6547 | 186.59
S02 | Kutch Solar Park | Gujarat | Solar | 2026-06 | 5472 | 155.95
S02 | Kutch Solar Park | Gujarat | Solar | 2026-07 | 5357 | 152.67
S02 | Kutch Solar Park | Gujarat | Solar | 2026-08 | 5654 | 161.14
S02 | Kutch Solar Park | Gujarat | Solar | 2026-09 | 6048 | 172.37
S02 | Kutch Solar Park | Gujarat | Solar | 2026-10 | 6547 | 186.59
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-04 | 3780 | 117.18
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-05 | 4092 | 126.85
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-06 | 3420 | 106.02
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-07 | 3348 | 103.79
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-08 | 3534 | 109.55
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-09 | 3780 | 117.18
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-10 | 4092 | 126.85
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-04 | 4536 | 138.35
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-05 | 4910 | 149.75
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-06 | 4104 | 125.17
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-07 | 4018 | 122.55
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-08 | 4241 | 129.35
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-09 | 4536 | 138.35
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-10 | 4910 | 149.75
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-04 | 3024 | 96.77
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-05 | 3274 | 104.77
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-06 | 2736 | 87.55
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-07 | 2678 | 85.7
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-08 | 2827 | 90.46
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-09 | 3024 | 96.77
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-10 | 3274 | 104.77
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-04 | 2268 | 68.04
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-05 | 2455 | 73.65
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-06 | 2052 | 61.56
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-07 | 2009 | 60.27
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-08 | 2120 | 63.6
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-09 | 2268 | 68.04
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-10 | 2455 | 73.65
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-04 | 5292 | 153.47
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-05 | 5729 | 166.14
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-06 | 4788 | 138.85
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-07 | 4687 | 135.92
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-08 | 4948 | 143.49
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-09 | 5292 | 153.47
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-10 | 5729 | 166.14
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-04 | 6804 | 190.51
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-05 | 7366 | 206.25
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-06 | 6156 | 172.37
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-07 | 6026 | 168.73
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-08 | 6361 | 178.11
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-09 | 6804 | 190.51
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-10 | 7366 | 206.25
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-04 | 1512 | 49.9
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-05 | 1637 | 54.02
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-06 | 1368 | 45.14
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-07 | 1339 | 44.19
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-08 | 1414 | 46.66
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-09 | 1512 | 49.9
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-10 | 1637 | 54.02
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-04 | 6480 | 233.28
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-05 | 7142 | 257.11
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-06 | 7776 | 279.94
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-07 | 8482 | 305.35
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-08 | 8258 | 297.29
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-09 | 7128 | 256.61
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-10 | 6696 | 241.06
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-04 | 5400 | 202.5
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-05 | 5952 | 223.2
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-06 | 6480 | 243
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-07 | 7068 | 265.05
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-08 | 6882 | 258.07
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-09 | 5940 | 222.75
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-10 | 5580 | 209.25
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-04 | 4320 | 166.32
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-05 | 4762 | 183.34
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-06 | 5184 | 199.58
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-07 | 5654 | 217.68
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-08 | 5506 | 211.98
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-09 | 4752 | 182.95
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-10 | 4464 | 171.86
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-04 | 3240 | 119.88
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-05 | 3571 | 132.13
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-06 | 3888 | 143.86
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-07 | 4241 | 156.92
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-08 | 4129 | 152.77
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-09 | 3564 | 131.87
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-10 | 3348 | 123.88
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-04 | 11232 | 353.81
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-05 | 12053 | 379.67
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-06 | 12096 | 381.02
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-07 | 12499 | 393.72
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-08 | 12053 | 379.67
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-09 | 11664 | 367.42
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-10 | 11606 | 365.59
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-04 | 7488 | 232.13
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-05 | 8035 | 249.09
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-06 | 8064 | 249.98
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-07 | 8333 | 258.32
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-08 | 8035 | 249.09
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-09 | 7776 | 241.06
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-10 | 7738 | 239.88
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-04 | 259 | 8.81
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-05 | 268 | 9.11
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-06 | 245 | 8.33
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-07 | 238 | 8.09
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-08 | 253 | 8.6
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-09 | 259 | 8.81
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-10 | 268 | 9.11
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-04 | 194 | 6.79
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-05 | 201 | 7.04
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-06 | 184 | 6.44
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-07 | 179 | 6.26
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-08 | 190 | 6.65
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-09 | 194 | 6.79
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-10 | 201 | 7.04

## Raw_Actual
SiteID | Site | State | Technology | Month | ActualMWh | ActualRevenueLakh | CurtailmentMWh | OutageHours | VarianceMWh | AchievementPct | CurtailmentPct
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-04 | 7197 | 212.31 | 106 | 22
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-05 | 7668 | 226.21 | 90 | 29
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-06 | 7155 | 211.07 | 171 | 5
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-07 | 6723 | 198.33 | 281 | 9
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-08 | 6566 | 193.7 | 368 | 14
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-09 | 7741 | 228.36 | 60 | 23
S01 | Jodhpur Solar Park | Rajasthan | Solar | 2026-10 | 8454 | 249.39 | 286 | 6
S02 | Kutch Solar Park | Gujarat | Solar | 2026-04 | 6060 | 172.71 | 30 | 40
S02 | Kutch Solar Park | Gujarat | Solar | 2026-05 | 5886 | 167.75 | 170 | 12
S02 | Kutch Solar Park | Gujarat | Solar | 2026-06 | 4826 | 137.54 | 164 | 6
S02 | Kutch Solar Park | Gujarat | Solar | 2026-07 | 4709 | 134.21 | 32 | 31
S02 | Kutch Solar Park | Gujarat | Solar | 2026-08 | 5094 | 145.18 | 322 | 8
S02 | Kutch Solar Park | Gujarat | Solar | 2026-09 | 5770 | 164.44 | 151 | 38
S02 | Kutch Solar Park | Gujarat | Solar | 2026-10 | 6115 | 174.28 | 242 | 25
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-04 | 3512 | 108.87 | 178 | 31
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-05 | 4149 | 128.62 | 147 | 2
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-06 | 3543 | 109.83 | 123 | 40
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-07 | 3013 | 93.4 | 127 | 29
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-08 | 3212 | 99.57 | 92 | 19
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-09 | 3761 | 116.59 | 38 | 40
S03 | Solapur Solar Park | Maharashtra | Solar | 2026-10 | 4235 | 131.28 | 172 | 5
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-04 | 4169 | 127.15 | 86 | 28
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-05 | 4610 | 140.6 | 231 | 27
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-06 | 3677 | 112.15 | 172 | 28
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-07 | 3805 | 116.05 | 40 | 27
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-08 | 3762 | 114.74 | 153 | 16
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-09 | 4132 | 126.03 | 41 | 32
S04 | Pavagada Solar Park | Karnataka | Solar | 2026-10 | 5121 | 156.19 | 69 | 26
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-04 | 2897 | 92.7 | 154 | 15
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-05 | 3087 | 98.78 | 187 | 2
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-06 | 2624 | 83.97 | 145 | 4
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-07 | 2673 | 85.54 | 153 | 11
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-08 | 2437 | 77.98 | 136 | 12
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-09 | 2359 | 75.49 | 112 | 120
S05 | Kamuthi Solar Park | Tamil Nadu | Solar | 2026-10 | 3385 | 108.32 | 174 | 27
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-04 | 2214 | 66.42 | 93 | 18
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-05 | 2160 | 64.8 | 59 | 35
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-06 | 2085 | 62.55 | 14 | 22
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-07 | 1690 | 50.7 | 0 | 14
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-08 | 2184 | 65.52 | 81 | 40
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-09 | 2182 | 65.46 | 5 | 4
S06 | Mahbubnagar Solar Park | Telangana | Solar | 2026-10 | 2541 | 76.23 | 47 | 19
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-04 | 4720 | 136.88 | 26 | 39
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-05 | 5139 | 149.03 | 258 | 13
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-06 | 4027 | 116.78 | 129 | 36
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-07 | 4593 | 133.2 | 187 | 28
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-08 | 4943 | 143.35 | 242 | 23
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-09 | 5139 | 149.03 | 175 | 6
S07 | Anantapur Solar Park | Andhra Pradesh | Solar | 2026-10 | 5592 | 162.17 | 246 | 3
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-04 | 6974 | 195.27 | 191 | 19
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-05 | 7093 | 198.6 | 22 | 35
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-06 | 5848 | 163.74 | 259 | 18
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-07 | 6128 | 171.58 | 229 | 11
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-08 | 6291 | 176.15 | 242 | 10
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-09 | 5954 | 166.71 | 286 | 33
S08 | Rewa Solar Park | Madhya Pradesh | Solar | 2026-10 | 6917 | 193.68 | 22 | 20
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-04 | 1356 | 44.75 | 88 | 40
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-05 | 1716 | 56.63 | 54 | 11
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-06 | 1311 | 43.26 | 4 | 3
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-07 | 1127 | 37.19 | 21 | 11
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-08 | 1302 | 42.97 | 3 | 13
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-09 | 1433 | 47.29 | 86 | 37
S09 | Jhansi Solar Park | Uttar Pradesh | Solar | 2026-10 | 1414 | 46.66 | 90 | 0
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-04 | 6551 | 235.84 | 26 | 26
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-05 | 6149 | 221.36 | 386 | 39
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-06 | 7753 | 279.11 | 327 | 8
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-07 | 7295 | 262.62 | 1527 | 21
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-08 | 7614 | 274.1 | 198 | 37
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-09 | 6814 | 245.3 | 285 | 35
W01 | Kutch Wind Farm | Gujarat | Wind | 2026-10 | 6850 | 246.6 | 362 | 6
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-04 | 5292 | 198.45 | 184 | 16
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-05 | 6226 | 233.47 | 202 | 35
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-06 | 6214 | 233.03 | 253 | 10
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-07 | 6503 | 243.86 | 375 | 28
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-08 | 7068 | 265.05 | 303 | 1
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-09 | 5821 | 218.29 | 279 | 28
W02 | Tirunelveli Wind Farm | Tamil Nadu | Wind | 2026-10 | 4961 | 186.04 | 84 | 9
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-04 | 3879 | 149.34 | 86 | 6
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-05 | 4291 | 165.2 | 138 | 29
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-06 | 5293 | 203.78 | 135 | 25
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-07 | 5349 | 205.94 | 68 | 6
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-08 | 5269 | 202.86 | 314 | 36
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-09 | 4861 | 187.15 | 67 | 40
W03 | Satara Wind Farm | Maharashtra | Wind | 2026-10 | 4308 | 165.86 | 71 | 10
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-04 | 2848 | 105.38 | 152 | 40
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-05 | 3017 | 111.63 | 114 | 7
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-06 | 3911 | 144.71 | 140 | 23
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-07 | 4445 | 164.47 | 233 | 34
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-08 | 3894 | 144.08 | 194 | 14
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-09 | 3179 | 117.62 | 192 | 38
W04 | Chitradurga Wind Farm | Karnataka | Wind | 2026-10 | 3261 | 120.66 | 77 | 34
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-04 | 10715 | 337.52 | 517 | 21
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-05 | 12282 | 386.88 | 121 | 9
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-06 | 10620 | 334.53 | 653 | 27
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-07 | 12149 | 382.69 | 62 | 34
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-08 | 11438 | 360.3 | 60 | 11
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-09 | 12212 | 384.68 | 327 | 25
H01 | Bikaner Hybrid Park | Rajasthan | Hybrid | 2026-10 | 11281 | 355.35 | 464 | 14
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-04 | 7136 | 221.22 | 52 | 14
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-05 | 8260 | 256.06 | 281 | 15
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-06 | 7951 | 246.48 | 411 | 39
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-07 | 8558 | 265.3 | 342 | 28
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-08 | 7553 | 234.14 | 104 | 34
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-09 | 8033 | 249.02 | 140 | 35
H02 | Kutch Hybrid Park | Gujarat | Hybrid | 2026-10 | 7181 | 222.61 | 209 | 20
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-04 | 245 | 8.33 | 7 | 17
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-05 | 239 | 8.13 | 0 | 31
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-06 | 251 | 8.53 | 14 | 38
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-07 | 205 | 6.97 | 11 | 31
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-08 | 223 | 7.58 | 2 | 24
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-09 | 260 | 8.84 | 8 | 14
R01 | Dubai Rooftop Solar | UAE | Rooftop | 2026-10 | 244 | 8.3 | 0 | 12
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-04 | 172 | 6.02 | 7 | 19
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-05 | 205 | 7.17 | 5 | 6
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-06 | 181 | 6.33 | 2 | 29
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-07 | 169 | 5.92 | 3 | 23
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-08 | 167 | 5.84 | 6 | 35
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-09 | 196 | 6.86 | 1 | 15
R02 | Singapore Rooftop Solar | Singapore | Rooftop | 2026-10 | 206 | 7.21 | 8 | 21

## Monthly
Month | Days | PlannedMWh | ActualMWh | VarianceMWh | AchievementPct | PlannedRevenueLakh | ActualRevenueLakh | RevenueAchievementPct | CurtailmentMWh | OutageHours | AvailabilityPct
2026-04 | 30
2026-05 | 31
2026-06 | 30
2026-07 | 31
2026-08 | 31
2026-09 | 30
2026-10 | 31
TOTAL

## State
State | Sites | PlannedMWh | ActualMWh | AchievementPct | PlannedRevenueLakh | ActualRevenueLakh | RevenueAchievementPct | CurtailmentMWh | OutageHours
Rajasthan
Gujarat
Maharashtra
Karnataka
Tamil Nadu
Telangana
Andhra Pradesh
Madhya Pradesh
Uttar Pradesh
UAE
Singapore
TOTAL

## Technology
Technology | Sites | PlannedMWh | ActualMWh | AchievementPct | PlannedRevenueLakh | ActualRevenueLakh | RevenueAchievementPct | CurtailmentMWh | OutageHours
Solar
Wind
Hybrid
Rooftop
TOTAL

## Checks
Check | Expected | Got | Diff | Status
Raw_Plan row count (sites x months) | 119
Raw_Actual row count (sites x months) | 119
Monthly planned total ties to Raw_Plan
Monthly actual total ties to Raw_Actual
State planned total ties to Raw_Plan
Technology actual total ties to Raw_Actual
Rows with negative actual generation | 0
Achievement % outside 0-150% | 0